## Implementation Plan
General Information | Value
Implementation Plan for: | IDEPC FHIR STI Rhapsody Route
Implementation Plan Author: | Dan Norman
IT Supervisor: | Mark Doerr
Task Order | Action | Owner | Team | Date | Planned Start Time (24 Hour Clock) | Planned End Time (24 Hour Clock) | Notes and Links
1. Pre-Implemention Work
This Section lists preparatory work done before implementation
1.01 | CREATE change management ticket | Dan Norman | Intergration Services | 2024-09-05
2. Pre-Install Work
This Section details work that occurs 30 - 60 minutes before the implementation commences.
2.01 | N/A
3. Implementation Plan
This Section details the sequential steps of implementing the application or other system change
3.01 | NOTIFY stakeholders and implementation team that implementation is starting | Dan Norman | Intergration Services | 2024-09-12 | 9:00 | 9:15
3.02 | Create RLC of Rhapsody STG Route | Dan Norman | Intergration Services | 2024-09-12 | 9:15 | 9:45
3.03 | Upload RLC to Rhapsody PRD | Dan Norman | Intergration Services | 2024-09-12 | 9:15 | 9:45
3.04 | Update Routing Table entires to enable PRD routing | Dan Norman | Intergration Services | 2024-09-12 | 9:15 | 9:45
4. Post-Implemention Plan Testing
This Section lists all the post - implementation steps to test for user / management acceptance
4.01 | N/A
5. Post Work
This section lists all the work to be done after completion of the implementation.
5.01 | NOTIFY stakeholders and implementation team that implementation is complete | Dan Norman | Intergration Services | 2024-09-12 | 9:45 | 10:00
5.02 | Confirm data has been sent | Dan Norman | Intergration Services | 2024-09-12 | 9:45 | 10:00
5.02 | CLOSE CM ticket | Dan Norman | Intergration Services | 2024-09-12 | 9:45 | 10:00
6. Backout Plan
This Section lists all the steps to roll back the implementation per the criteria in Section 3
6.01 | Revert Route Table entry change to disable PRD routing | Dan Norman | Intergration Services
6.02 | Delete route and related items from Rhapsody PRD | Dan Norman | Intergration Services